TOBB ETÜ

Economy & Technology University

BIL 495 / YAP 495

# Project Management Plan (PMP)

Reference: IEEE 1058 / ISO/IEC 12207

# Document Control

| Document Title | Project Management Plan |
| --- | --- |
| Document ID | PMP-AICG-2025-001 |
| Project Name | AI-Based Adaptive Course Generator |
| Prepared By | KoRN Project Team |
| Preparation Date | 28.12.2025 |
| Version | 1.0 |
| Project Phase | Planning / Pre-Implementation |

# 1. Project Overview

## 1.1 Project Goals

The AI-Based Adaptive Course Generator project aims to develop an AI-driven web platform that dynamically generates educational lessons, quizzes, and adaptive assessments based on user input and learning performance. The system will leverage Large Language Models (LLMs) and semantic retrieval techniques to create personalized learning experiences that adapt to individual user needs.

## 1.2 Project Objectives

- Develop a functional web-based educational platform using Streamlit and FastAPI

- Implement AI-powered lesson generation using OpenAI's LLM API

- Create an adaptive learning system using EMA-based mastery tracking

- Integrate semantic retrieval using FAISS vector database

- Implement prompt caching to optimize API costs

- Achieve ≥90% unit test coverage

## 1.3 Deliverables

| Deliverable | Description |
| --- | --- |
| Web Application | Fully functional AI-based course generator platform |
| SRS Document | Software Requirements Specification |
| SAD Document | System Architecture Document |
| SDD Document | Software Design Description |
| STP Document | Software Test Plan |
| QMP Document | Quality Management Plan |
| Source Code | Complete source code repository on GitHub |
| User Documentation | User manual and API documentation |

## 1.4 Stakeholders

| Stakeholder | Role | Interest |
| --- | --- | --- |
| Project Team | Development | Successful project completion |
| Project Supervisor | Guidance & Evaluation | Quality and academic standards |
| End Users | Students/Learners | Effective learning experience |
| TOBB ETÜ | Academic Institution | Academic excellence |

# 2. Organization and Roles

## 2.1 Team Structure

| Team Member | Role | Responsibilities |
| --- | --- | --- |
| Ahmet | Lead Developer / QA | Full-stack development, Unit/Integration/System testing, Code review |
| Emre Ekşi | Test Lead / Developer | Test planning, Test documentation, Backend development |
| KoRN Team | Project Team | Documentation, Architecture design, Project coordination |

## 2.2 Communication Plan

- Weekly Team Meetings: Regular progress reviews and planning sessions

- Supervisor Meetings: Bi-weekly progress reports and guidance sessions

- Version Control: GitHub for code collaboration with feature-branch workflow

- Issue Tracking: GitHub Issues for defect tracking and task management

# 3. Project Schedule

## 3.1 Project Timeline

| Phase | Start Date | End Date | Status |
| --- | --- | --- | --- |
| Requirements Analysis | Jan 6, 2026 | Jan 19, 2026 | Planned |
| System Design | Jan 20, 2026 | Feb 2, 2026 | Planned |
| Implementation - Phase 1 | Feb 3, 2026 | Feb 23, 2026 | Planned |
| Implementation - Phase 2 | Feb 24, 2026 | Mar 15, 2026 | Planned |
| Unit Testing | Mar 16, 2026 | Mar 22, 2026 | Planned |
| Integration Testing | Mar 23, 2026 | Mar 29, 2026 | Planned |
| System Testing | Mar 30, 2026 | Apr 5, 2026 | Planned |
| Acceptance Testing | Apr 6, 2026 | Apr 12, 2026 | Planned |
| Documentation & Finalization | Apr 13, 2026 | Apr 26, 2026 | Planned |
| Final Presentation | Apr 27, 2026 | May 3, 2026 | Planned |

## 3.2 Milestones

| Milestone | Target Date | Status |
| --- | --- | --- |
| M1: Requirements Approved | Jan 19, 2026 | Planned |
| M2: Architecture Design Complete | Feb 2, 2026 | Planned |
| M3: MVP Development Complete | Mar 15, 2026 | Planned |
| M4: Testing Complete | Apr 12, 2026 | Planned |
| M5: Project Delivery | May 3, 2026 | Planned |

# 4. Budget and Resources

## 4.1 Resource Allocation

Human Resources:

- Development Team: 2-3 team members

- Estimated effort: ~400 person-hours over project duration

Technical Resources:

- Development hardware: Personal computers

- Cloud services: Local deployment (minimal cost)

- Version control: GitHub (free tier)

- OpenAI API: Pay-per-use model with prompt caching to reduce costs

## 4.2 Technology Stack

| Component | Technology |
| --- | --- |
| Frontend | Streamlit |
| Backend | FastAPI (Python) |
| Database | SQLite |
| Vector Database | FAISS |
| AI Services | OpenAI API |
| Version Control | Git / GitHub |

# 5. Risk Management

## 5.1 Risk Register

| ID | Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R1 | API Cost Overrun | Medium | High | Implement SHA-256 prompt caching (~40% cost reduction) |
| R2 | AI Hallucinations | Medium | Medium | Factual checks, prompt tuning, context grounding with FAISS |
| R3 | API Latency | Medium | Medium | Response caching, async processing, timeout handling |
| R4 | Technical Complexity | Low | High | Modular architecture, incremental development, early prototyping |
| R5 | Schedule Delay | Medium | High | Buffer time in schedule, scope adjustment if needed |
| R6 | Resource Constraints | Low | Medium | Prioritize core features, use lightweight tools |

# 6. Quality Assurance

## 6.1 Quality Objectives

| Metric | Target | Measurement |
| --- | --- | --- |
| Unit Test Coverage | ≥ 90% | coverage.py |
| Response Time | ≤ 2 sec (target), ≤ 3 sec (max) | Performance testing |
| Output Correctness | ≥ 95% | Requirement-based scenarios |
| Fault Density | < 0.5 per module | Defect tracking |

## 6.2 Testing Strategy

- Unit Testing: Individual components will be tested using pytest/unittest

- Integration Testing: Testing interactions between FastAPI, FAISS, and LLM adapters

- System Testing: End-to-end validation of Topic→Lesson→Quiz→Feedback flow

- Acceptance Testing: Final validation through demo and supervisor evaluation

## 6.3 Review Process

- Code reviews will be conducted for all merge requests

- Document reviews before submission

- Supervisor approval for major deliverables

- Continuous integration and automated testing will be implemented

# 7. Appendix

Related Documents:

- Software Requirements Specification (SRS)

- System Architecture Document (SAD)

- Software Design Description (SDD)

- Software Test Plan (STP)

- Quality Management Plan (QMP)

- Bitirme Projeleri Kılavuz 2025

# 8. References

- IEEE 1058 - Standard for Software Project Management Plans

- ISO/IEC 12207 - Software Life Cycle Processes

- ISO 9001 - Quality Management Systems

- PMBOK Guide - Project Management Body of Knowledge